## Version
Version | Date | Comment | User
1.0 | 6/26/2018 | - initial creation - created tests for COM_Configurator | CST
2.0 | 7/23/2018 | - added tests for the rest of requirements | CST

## Overview
Requirements | Description | Test(s) | Result | Implemented | Passed
| Check the tool functionality | Test 1: Call the tool using only the NeMo parameter | - check that the tool will output only the file ComCallout.xml | not done | NO
TRS.COMCONF.INOUT.001 |  | Test 2: Call the tool using only the EnGw parameter | - check that the tool will output the files: EcuC.epc, PduR.epc, EnGwCCB.epc, EnGwCCD.epc, EnGwCCLD.epc, EnGwCLD.epc, EnGwFonc.epc | not done | NO
|  | Test 3: Call the tool using both EnGw and NeMo parameters | - check that the tool will ouput all the above mentioned files | not done | NO
|  | Test 4: Call the tool without any of the above mentioned parameters | - check that the tool will not output any of the above mentioned files | not done | NO
TRS.COMCONF.GEN.001(0) | Check the input files | Covered by the tests below |  | not done | NO
TRS.COMCONF.GEN.002(0) | Check the output file | Covered by the tests below |  | not done | NO
TRS.COMCONF.GEN.003(0) | Check the format of the ComCallout file | Can not be tested |  | not done | NO
TRS.COMCONF.GEN.004(0) | Check if a <SPECIFIC-CALLOUT> contains a valid <PDU-REF>, the toll will generate the ComIPduCallout parameter | Test 1: provide to the tool a SPECIFIC-CALLOUT which has the PDU-REF tag set | - check that the tool will set the ComIPduCallout parameter | done | YES
|  | Test 12: provide to the tool a SPECIFIC-CALLOUT that has not the PDU-REF tag set | - check that the tool will not set the ComIPduCallout parameter | done | YES
TRS.COMCONF.GEN.005(0) | Check if a SPECIFIC-CALLOUT contains a valid SYSTEM-SIGNAL-REF, the toll will generate the ComTimeoutNotification and ComNotification parameter | Test 1: provide to the tool a SPECIFIC-CALLOUT which has a valid SYSTEM-SIGNAL-REF tag | - check that the tool will set the ComTimeoutNotification and ComNotification parameter | done | YES
|  | Test 2: provide to the tool a SPECIFIC-CALLOUT which has the <SYSTEM-SIGNAL-REF> tag set, but it does not exist a <SENDER-RECEIVER-TO-SIGNAL-MAPPING> tag from System Generated file which have the same SYSTEM-SIGNAL-REF tag | - check that the tool will not set the ComTimeoutNotification and ComNotification parameter | done | YES
|  | Test 3: provide to the tool a SPECIFIC-CALLOUT that has no SYSTEM-SIGNAL-REF tag | - check that the tool will not set the ComTimeoutNotification and ComNotification parameter | done | YES
TRS.COMCONF.GEN.006(0) | Check the input files | Covered by the tests below |  | not done | NO
TRS.COMCONF.GEN.007(0) | Check the output files | Covered by the tests below |  | not done | NO
TRS.COMCONF.GEN.008(0) | Check the format of the PduRconfiguration script | Can not be tested |  | not done | NO
TRS.COMCONF.GEN.009(0) | Check if each <GATEWAY-MAPPING> will be analysed | Can not be tested |  | not done | NO
TRS.COMCONF.GEN.010(0) | Check if each <SOURCE-I-PDU-REF> and <TARGET-I-PDU-REF> will have the following information present in the messagery file: Cluster, PDU ID, Transmission direction | Test 1: provide to the tool only one <SOURCE-I-PDU-REF>. That source has a CLUSTER and a Transmission direction, but no PDU ID | - check that the EnGw_PduR_Update.xml file will no set the PduRDestPdu parameter | done | YES
|  | Test 2: provide to the tool only one <SOURCE-I-PDU-REF>. That source has a CLUSTER and a PDU ID, but no Transmission direction | - check that the EnGw_PduR_Update.xml file will no set the PduRDestPdu parameter | done | YES
|  | Test 3: provide to the tool only one <SOURCE-I-PDU-REF>. That source has a CLUSTER,a PDU ID and a Transmission direction | - check that the EnGw_PduR_Update.xml file will set the PduRDestPdu parameter | done | YES
TRS.COMCONF.GEN.011(0) | Check if only <SOURCE-I-PDU-REF> that have the transmission direction established will be present in the output file | Test 1: provide to the tool only one <SOURCE-I-PDU-REF>. That source has a Transmission direction | - check that the EnGw_PduR_Update.xml file will set the PduRDestPdu parameter | done | YES
|  | Test 2: provide to the tool only one <SOURCE-I-PDU-REF>. That source has no Transmission direction | - check that the EnGw_PduR_Update.xml file will no set the PduRDestPdu parameter | done | YES
TRS.COMCONF.GEN.012(0) | Check if only the next <GATEWAY-MAPPING> types will be present in the output file: GW-REMOTE-DIAG, GW-FILTERED, GW-LIN-UNCONNECTED, GW-CAN-DIAG | Test 1: provide to the tool all types for <GATEWAY-MAPPING> | - check that the EnGw_PduR_Update.xml file will set the PduRDestPdu parameter for each <SOURCE-I-PDU-REF> | done | YES
|  | Test 2: provide to the tool a different type for <GATEWAY-MAPPING> | - check that the EnGw_PduR_Update.xml file will not set the PduRDestPdu parameter | done | YES
TRS.COMCONF.GEN.013(0) | Check the format of the PduR.epc file | Can not be tested |  | not done | NO
TRS.COMCONF.GEN.014(0) | Check if each <GATEWAY-MAPPING> will be analysed | Can not be tested |  | not done | NO
TRS.COMCONF.GEN.015(0) | Check if each <SOURCE-I-PDU-REF> and <TARGET-I-PDU-REF> will have the following information present in the messagery file: PDU ID and Transmission direction | Test 1: provide to the tool only one <GATEWAY-MAPPING> which has a <SOURCE-I-PDU-REF> and a <TARGET-I-PDU-REF>. The <SOURCE-I-PDU-REF> has a valid PDU ID, but no Transmission direction. The <TARGET-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. | - check that the routing path will not be created | done | YES
|  | Test 2: provide to the tool only one <GATEWAY-MAPPING> which has a <SOURCE-I-PDU-REF> and a <TARGET-I-PDU-REF>. The <SOURCE-I-PDU-REF> has a valid Transmission direction,but no PDU ID. The <TARGET-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. | - check that the routing path will not be created | done | YES
|  | Test 3: provide to the tool only one <GATEWAY-MAPPING> which has a <SOURCE-I-PDU-REF> and a <TARGET-I-PDU-REF>. The <SOURCE-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. The <TARGET-I-PDU-REF> has a valid PDU ID, but no Transmission direction. | - check that the routing path will not be created | done | YES
|  | Test 4: provide to the tool only one <GATEWAY-MAPPING> which has a <SOURCE-I-PDU-REF> and a <TARGET-I-PDU-REF>. The <SOURCE-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. The <TARGET-I-PDU-REF> has a valid Transmission direction,but no PUD ID. | - check that the routing path will not be created | done | YES
|  | Test 4: provide to the tool only one <GATEWAY-MAPPING> which has a <SOURCE-I-PDU-REF> and a <TARGET-I-PDU-REF>. The <SOURCE-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. The <TARGET-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. | - check that the routing path will be created | done | YES
TRS.COMCONF.GEN.016(0) | Check if only the next <GATEWAY-MAPPING> types will be present in the output file: GW-REMOTE-DIAG, GW-FILTERED, GW-LIN-UNCONNECTED, GW-CAN-DIAG | Test 1: provide to the tool all types for <GATEWAY-MAPPING> | - check that the PduR.epc file will set the routing paths for each <GATEWAY-MAPPING> | done | YES
|  | Test 2: provide to the tool a different type for <GATEWAY-MAPPING> | - check that the Pdu.epc file will not set a routing path for <GATEWAY-MAPPING> | done | YES
TRS.COMCONF.GEN.017(0) | Check if for each target found in a valid <GATEWAY-MAPPING>, a routing path will be created with the following name: PduRRoutingPath_<source_name> | Test 1: provide to the tool a valid <GATEWAY-MAPPING> | - check that the PduR.epc file will set a routing path for that <GATEWAY-MAPPING> with the corect name | done | YES
TRS.COMCONF.GEN.018(0) | Check if for each target found in a valid <GATEWAY-MAPPING>, the content of the routing path is the same as in PduR.epc example | Test 1: provide to the tool a valid <GATEWAY-MAPPING> | - check that the PduR.epc file will set a routing path with the corect content | done | YES
TRS.COMCONF.GEN.019(0) | Check if for each target found in a valid <GATEWAY-MAPPING>, a routing path will be created with the following name: PduRRoutingPath_<source_name>_<target_name>_FROM_CDD | Test 1: provide to the tool a valid <GATEWAY-MAPPING> | - check that the PduR.epc file will set a routing path for each target found with the corect name | done | YES
TRS.COMCONF.GEN.020(0) | Check if for each target found in a valid <GATEWAY-MAPPING>, the content of the routing path is the same as in PduR.epc example | Test 1: provide to the tool a valid <GATEWAY-MAPPING> | - check that the PduR.epc file will set a routing path with the corect content | done | YES
TRS.COMCONF.GEN.021(0) | Check if for each configured LIN 1.3 network found in the entry data, a routing path will be created with the following name: PduRRoutingPath_EnGw_LinIf_REQ_<network_name>_1P3 | Test 1: provide to the tool a valid LIN 1.3 network | - check that the PduR.epc file will set a routing path with the corect name | done | YES
TRS.COMCONF.GEN.022(0) | Check if for each configured LIN 1.3 network found in the entry data, the content of the routing path is the same as in PduR.epc example | Test 1: provide to the tool a valid LIN 1.3 network | - check that the PduR.epc file will set a routing path with the corect content | done | YES
TRS.COMCONF.GEN.023(0) | Check if for each configured LIN 1.3 network found in the entry data, a routing path will be created with the following name: PduRRoutingPath_EnGw_LinIf_REP_<network_name>_1P3 | Test 1: provide to the tool a valid LIN 1.3 network | - check that the PduR.epc file will set a routing path with the corect name | done | YES
TRS.COMCONF.GEN.024(0) | Check if for each configured LIN 1.3 network found in the entry data, the content of the routing path is the same as in PduR.epc example | Test 1: provide to the tool a valid LIN 1.3 network | - check that the PduR.epc file will set a routing path with the corect content | done | YES
TRS.COMCONF.GEN.025(0) | Check if for each configured ECU that is connected to LIN 2.1 network found in the entry data, a routing path will be created with the following name: PduRRoutingPath_EnGw_LinTp_REQ_<ECU_name>_<network_name> | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network | - check that the PduR.epc file will set a routing path with the corect name | done | YES
TRS.COMCONF.GEN.026(0) | Check if for each configured ECU that is connected to a LIN 2.1 network found in the entry data, the content of the routing path is the same as in PduR.epc example | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network | - check that the PduR.epc file will set a routing path with the corect content | done | YES
TRS.COMCONF.GEN.027(0) | Check if for each configured ECU that is connected to LIN 2.1 network found in the entry data, a routing path will be created with the following name: PduRRoutingPath_EnGw_LinTp_REP_<ECU_name>_<network_name> | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network | - check that the PduR.epc file will set a routing path with the corect name | done | YES
TRS.COMCONF.GEN.028(0) | Check if for each configured ECU that is connected to a LIN 2.1 network found in the entry data, the content of the routing path is the same as in PduR.epc example | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network | - check that the PduR.epc file will set a routing path with the corect content | done | YES
TRS.COMCONF.GEN.029(0) | Check if for each configured ECU that is connected to a LIN 1.3 network found in the entry data and for each configured DIAG network, a routing path will be created with the following name: PduRRoutingPath_EnGw_CanIf_REQ_<DIAG_network>_<ECU_name>_<network_name> | Test 1: provide to the tool a valid ECU that is connected to a LIN 1.3 network and a DIAG network | - checK that the PduR.epc file will set a routing path with the corect name | done | YES
TRS.COMCONF.GEN.030(0) | Check if for each configured ECU that is connected to a LIN 1.3 network found in the entry data and for each configured DIAG network, the content of the routing path is the same as in PduR.epc example | Test 1: provide to the tool a valid ECU that is connected to a LIN 1.3 network and a DIAG network | - check that the PduR.epc file will set a routing path with the corect content | done | YES
TRS.COMCONF.GEN.031(0) | Check if for each configured ECU that is connected to a LIN 1.3 network found in the entry data and for each configured DIAG network, a routing path will be created with the following name: PduRRoutingPath_EnGw_CanIf_REP_<DIAG_network>_<ECU_name>_<network_name> | Test 1: provide to the tool a valid ECU that is connected to a LIN 1.3 network and a DIAG network | - checK that the PduR.epc file will set a routing path with the corect name | done | YES
TRS.COMCONF.GEN.032(0) | Check if for each configured ECU that is connected to a LIN 1.3 network found in the entry data and for each configured DIAG network, the content of the routing path is the same as in PduR.epc example | Test 1: provide to the tool a valid ECU that is connected to a LIN 1.3 network and a DIAG network | - check that the PduR.epc file will set a routing path with the corect content | done | YES
TRS.COMCONF.GEN.033(0) | Check if for each configured ECU that is connected to a LIN 2.1 network found in the entry data and for each configured DIAG network, a routing path will be created with the following name: PduRRoutingPath_EnGw_CanTp_REQ_<DIAG_network>_<ECU_name>_<network_name> | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network and a DIAG network | - checK that the PduR.epc file will set a routing path with the corect name | done | YES
TRS.COMCONF.GEN.034(0) | Check if for each configured ECU that is connected to a LIN 2.1 network found in the entry data and for each configured DIAG network, the content of the routing path is the same as in PduR.epc example | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network and a DIAG network | - check that the PduR.epc file will set a routing path with the corect content | done | YES
TRS.COMCONF.GEN.035(0) | Check if for each configured ECU that is connected to a LIN 2.1 network found in the entry data and for each configured DIAG network, a routing path will be created with the following name: PduRRoutingPath_EnGw_CanTp_REP_<DIAG_network>_<ECU_name>_<network_name> | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network and a DIAG network | - checK that the PduR.epc file will set a routing path with the corect name | done | YES
TRS.COMCONF.GEN.036(0) | Check if for each configured ECU that is connected to a LIN 2.1 network found in the entry data and for each configured DIAG network, the content of the routing path is the same as in PduR.epc example | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network and a DIAG network | - check that the PduR.epc file will set a routing path with the corect content | done | YES
TRS.COMCONF.GEN.037(0) | Check if the PduRSourcePduHandledId parameter found in the source section ot each routing path will be unique for each routing path, will start from 0 and will be continuous. | Test 1: provide to the tool all tree files with valid <GATEWAY-MAPPING>, <LIN-SLAVE-CONFIG> and <CAN-DIAG-TOOL> | - check that the PduR.epc file will meet the initial requirement | done | YES
TRS.COMCONF.GEN.038(0) | Check the input files | Covered by the tests below |  | not done | NO
TRS.COMCONF.GEN.039(0) | Check the output files | Covered by the tests below |  | not done | NO
TRS.COMCONF.GEN.040(0) | Check if the source and the target from mapping have an equivalent CAN-FRAME. If not, the mapping will not be taken into account | Test 1: provide to the tool a <GATEWAY-MAPPING>. The <SOURCE-I-PDU-REF> does not have an equivalent CAN-FRAME. | - check that the EcuC.epc will not contain that <GATEWAY-MAPPING> | done | YES
|  | Test 2: provide to the tool a <GATEWAY-MAPPING>. The <TARGET-I-PDU-REF> does not have an equivalent CAN-FRAME. | - check that the EcuC.epc will not contain that <GATEWAY-MAPPING> | done | YES
|  | Test 3: provide to the tool a <GATEWAY-MAPPING>. The <SOURCE-I-PDU-REF> and the <TARGET-I-PDU-REF> do not have an equivalent CAN-FRAME. | - check that the EcuC.epc will not contain that <GATEWAY-MAPPING> | done | YES
|  | Test 4:provide to the tool a <GATEWAY-MAPPING>. The <SOURTCE-I-PDU-REF> and the <TARGET-I-PDU-REF> have an equivalent CAN-FRAME. | - check that the EcuC.epc will contain that <GATEWAY-MAPPING> | done | YES
TRS.COMCONF.GEN.041(0) | Check if for each ECU connected to a LIN 2.1 network and each DIAG configured network,an PDU will be created with the following data: Name: EnGwCLD_REQ_<DIAG_network>_<ECU_name>_<network_name>_CanTp and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network and a DIAG network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.042(0) | Check if for each ECU connected to a LIN 2.1 network and each DIAG configured network,an PDU will be created with the following data: Name: CanTp_REQ_<DIAG_network>_<ECU_name>_<network_name>_EnGwCLD and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network and a DIAG network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.043(0) | Check if for each ECU connected to a LIN 2.1 network and each DIAG configured network,an PDU will be created with the following data: Name: EnGwCLD_REP_<DIAG_network>_<ECU_name>_<network_name>_CanTp and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network and a DIAG network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.044(0) | Check if for each ECU connected to a LIN 2.1 network and each DIAG configured network,an PDU will be created with the following data: Name: CanTp_REP_<DIAG_network>_<ECU_name>_<network_name>_EnGwCLD and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network and a DIAG network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.045(0) | Check if for each ECU connected to LIN 2.1 network, an PDU will be created with the following data: Name: EnGwCLD_REQ_<ECU_name>_<network_name>_LinTp and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.046(0) | Check if for each ECU connected to LIN 2.1 network, an PDU will be created with the following data: Name: LinTp_REQ_<ECU_name>_<network_name>_EnGwCLD and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.047(0) | Check if for each ECU connected to LIN 2.1 network, an PDU will be created with the following data: Name: EnGwCLD_REP_<ECU_name>_<network_name>_LinTp and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.048(0) | Check if for each ECU connected to LIN 2.1 network, an PDU will be created with the following data: Name: LinTp_REP_<ECU_name>_<network_name>_EnGwCLD and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 2.1 network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.049(0) | Check if for each ECU connected to a LIN 1.3 network and each DIAG configured network,an PDU will be created with the following data: Name: EnGwCLD_REQ_<DIAG_network>_<ECU_name>_<network_name>_CanIf and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 1.3 network and a DIAG network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.050(0) | Check if for each ECU connected to a LIN 1.3 network and each DIAG configured network,an PDU will be created with the following data: Name: CanIf_REQ_<DIAG_network>_<ECU_name>_<network_name>_EnGwCLD and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 1.3 network and a DIAG network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.051(0) | Check if for each ECU connected to a LIN 1.3 network and each DIAG configured network,an PDU will be created with the following data: Name: EnGwCLD_REP_<DIAG_network>_<ECU_name>_<network_name>_CanIf and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 1.3 network and a DIAG network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.052(0) | Check if for each ECU connected to a LIN 1.3 network and each DIAG configured network,an PDU will be created with the following data: Name: CanIf_REp_<DIAG_network>_<ECU_name>_<network_name>_EnGwCLD and PDU length: 8 | Test 1: provide to the tool a valid ECU that is connected to a LIN 1.3 network and a DIAG network | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.053(0) | Check if for each LIN 1.3 network configured that has at least one ECU connected to it, an PDU will be created with the following data: Name: EnGwCLD_REQ_<network>_1P3_LinIf and PDU length: 8 | Test 1: provide to the tool a LIN 1.3 network that has at least one ECU connected to it | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.054(0) | Check if for each LIN 1.3 network configured that has at least one ECU connected to it, an PDU will be created with the following data: Name: LinIf_REQ_<network>_1P3_EnGwCLD and PDU length: 8 | Test 1: provide to the tool a LIN 1.3 network that has at least one ECU connected to it | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.055(0) | Check if for each LIN 1.3 network configured that has at least one ECU connected to it, an PDU will be created with the following data: Name: EnGwCLD_REP_<network>_1P3_LinIf and PDU length: 8 | Test 1: provide to the tool a LIN 1.3 network that has at least one ECU connected to it | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.056(0) | Check if for each LIN 1.3 network configured that has at least one ECU connected to it, an PDU will be created with the following data: Name: LinIf_REP_<network>_1P3_EnGwCLD and PDU length: 8 | Test 1: provide to the tool a LIN 1.3 network that has at least one ECU connected to it | - check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.057(0) | Check if for each LIN 2.1 network configured that has at least one ECU connected to it, and each DIAG configured network, an PDU will be created with the following data: Name: CanIf_REQ_<DIAG_name>_network_name>_CanTp and PDU length: 8 | Test 1: provide to the tool a LIN 2.1 network that has at least one ECU connected to it and a DIAG network | '- check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.058(0) | Check if for each LIN 2.1 network configured that has at least one ECU connected to it, and each DIAG configured network, an PDU will be created with the following data: Name: CanTp_REP_<DIAG_name>_network_name>_CanIf and PDU length: 8 | Test 1: provide to the tool a LIN 2.1 network that has at least one ECU connected to it and a DIAG network | '- check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.059(0) | Check if for each LIN 2.1 network configured that has at least one ECU connected to it, and each DIAG configured network, an PDU will be created with the following data: Name: CanTp_REP_<DIAG_name>_<network_name>_<ECU_name>_CanIf and PDU length: 8 | Test 1: provide to the tool a LIN 2.1 network that has at least one ECU connected to it and a DIAG network | '- check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.060(0) | Check if for each LIN 2.1 network configured that has at least one ECU connected to it, and each DIAG configured network, an PDU will be created with the following data: Name: CanTp_FC_REP_<DIAG_name>_<network_name>_<ECU_name>_CanIf and PDU length: 8 | Test 1: provide to the tool a LIN 2.1 network that has at least one ECU connected to it and a DIAG network | '- check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.061(0) | Check if for each valid mapping found in mappings file, an PDU will be created with the following data: Name: <target_name>_TO_CDD and PDU length: 8 | Test 1: provide to the tool a valid <GATEWAY-MAPPING> | '- check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMOCNF.GEN.062(0) | Check if for each valid mapping found in mappings file, an PDU will be created with the following data: Name: <target_name>_FROM_CDD and PDU length: 8 | Test 1: provide to the tool a valid <GATEWAY-MAPPING> | '- check that the EcuC.epc file will set a PDU with the corect content | done | YES
TRS.COMCONF.GEN.003 | Check that the tool will propely create te PduRRountingTables | Test 1: provide to the tool one valid mapping, where the source frame is referenced in a cluster HS or DIAG | - check that the routing table is created with the correct name - check that the routing path is created with the correct name - check that the destination is created with the correct name and the correct parameters - check that the source is created with the correct name | not done | NO
|  | Test 2: provide to the tool one valid mapping, where the source frame is referenced in a cluster different than LIN, and the target-frame is referenced in a cluster HS or DIAG | - check that the routing table is created with the correct name - check that the routing path is created with the correct name - check that the destination is created with the correct name and the correct parameters - check that the source is created with the correct name | not done | NO
|  | Test 3: provide to the tool one valid mapping of type GW-BTA | - check that the routing table is created with the correct name - check that the routing path is created with the correct name - check that the destination is created with the correct name and the correct parameters - check that the source is created with the correct name | not done | NO
|  | Test 4: provide to the tool one valid mapping of type GW-ISACTIVE | - check that the routing table is created with the correct name - check that the routing path is created with the correct name - check that the destination is created with the correct name and the correct parameters - check that the source is created with the correct name | not done | NO
|  | Test 5: provide to the tool one valid mapping of type CCL-DIAG-GW | - check that the routing table is created with the correct name - check that the routing path is created with the correct name - check that the destination is created with the correct name and the correct parameters - check that the source is created with the correct name | not done | NO
|  | Test 6: provide to the tool one valid mapping of type GW-FILTERED, where the target frame and the source frame are+C60 referenced in a cluster of type FD | - check that the routing table is not created | not done | NO
TRS.COMCONF.GEN.005 | Check that the tool will create the CanTp PDUs | Test 1: provide to the tool one NAD configured in a 2.1 LIN network, and one Diag tool configured | -check that the four PDUs will be created for the specified NAD - check that the naming rule is respected for each PDU | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 1.3 LIN network, and one Diag tool configured | - check that no PDUs are created | not done | NO
TRS.COMCONF.GEN.006 | Check that the tool will create the LinTp PDUs | Test 1: provide to the tool one NAD configured in a 2.1 LIN network | -check that the four PDUs will be created for the specified NAD - check that the naming rule is respected for each PDU | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 1.3 LIN network | - check that no PDUs are created | not done | NO
TRS.COMCONF.GEN.007 | Check that the tool will create the LIN type 2.1 PDUs | Test 1: provide to the tool one 2.1 LIN, and one Diag tool configured | -check that the two PDUs will be created for the specified NAD - check that the naming rule is respected for each PDU | not done | NO
|  | Test 2: provide to the tool one 1.3 LIN, and one Diag tool configured | - check that no PDUs are created | not done | NO
TRS.COMCONF.GEN.008 | Check that the tool will create the CanIf PDUs | Test 1: provide to the tool one NAD configured in a 1.3 LIN network, and one Diag tool configured | -check that the four PDUs will be created for the specified NAD - check that the naming rule is respected for each PDU | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 2.1 LIN network, and one Diag tool configured | - check that no PDUs are created | not done | NO
TRS.COMCONF.GEN.009 | Check that the tool will create the LinIf PDUs | Test 1: provide to the tool one NAD configured in a 1.3 LIN network | -check that the four PDUs will be created for the specified network - check that the naming rule is respected for each PDU | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 2.1 LIN network | - check that no PDUs are created | not done | NO
TRS.COMCONF.GEN.00B | Check that the CanTp frames are created | Test 1: provide to the tool one NAD configured in a 2.1 LIN network, and one Diag tool configured | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 1.3 LIN network, and one Diag tool configured | - check that no frame is created for the specified NAD | not done | NO
TRS.COMCONF.GEN.00C | Check that the LinTp frames are created | Test 1: provide to the tool one NAD configured in a 2.1 LIN network | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 1.3 LIN network | - check that no frame is created for the specified NAD | not done | NO
TRS.COMCONF.GEN.00D | Check that the CanIf frames are created | Test 1: provide to the tool one NAD configured in a 1.3 LIN network, and one Diag tool configured | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 2.1 LIN network, and one Diag tool configured | - check that no frame is created for the specified NAD | not done | NO
TRS.COMCONF.GEN.00E | Check that the LinIf frames are created | Test 1: provide to the tool one NAD configured in a 2.1 LIN network | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 1.3 LIN network | - check that no frame is created for the specified NAD | not done | NO
TRS.COMCONF.GEN.01F | Check that CCLD gateway frames are created | Test 1: provide one valid mapping of type CCL-DIAG-GW, where the source and target frames are referenced in the cluster | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one valid mapping with type different than CCL-DIAG-GW, where the source and target frames are referenced in the cluster | - check that no frames are created for the specified mapping | not done | NO
TRS.COMCONF.GEN.02F | Check that CCB gateway frames are created | Test 1: provide one valid mapping of type GW-BTA, where the source and target frames are referenced in the cluster | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one valid mapping with type different than GW-BTA, where the source and target frames are referenced in the cluster | - check that no frames are created for the specified mapping | not done | NO
TRS.COMCONF.GEN.03F | Check that CCD gateway frames are created | Test 1: provide one valid mapping of type GW-CAN-DIAG, where the source and target frames are referenced in the cluster | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one valid mapping with type different than GW-CAN-DIAG, where the source and target frames are referenced in the cluster | - check that no frames are created for the specified mapping | not done | NO
TRS.COMCONF.GEN.04F | Check that Fonc gateway frames are created | Test 1: provide one valid mapping of type GW-ISACTIVE, where the source and target frames are referenced in the cluster | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one valid mapping with type different than GW-ISACTIVE, where the source and target frames are referenced in the cluster | - check that no frames are created for the specified mapping | not done | NO
CHECK.XML | Check the tool behavior in case of xml file not well formed | Provide to the tool one ".xml" or ".arxml" file that is not correct (tags not properly closed, multiple roots, etc) | - check that no file is generated | not done | NO