## Version
Version | Date | Comment | User
1.0 | 6/26/2018 | - initial creation - created tests for COM_Configurator | CST
2.0 | 7/23/2018 | - added tests for the rest of requirements | CST

## Overview
Requirements | Description | Test(s) | Result | Implemented | Passed
| Check the tool functionality | Test 1: Call the tool using only the NeMo parameter | - check that the tool will output only the file ComCallout.xml | not done | NO
TRS.COMCONF.INOUT.001 |  | Test 2: Call the tool using only the EnGw parameter | - check that the tool will output the files: EcuC.epc, PduR.epc, EnGwCCB.epc, EnGwCCD.epc, EnGwCCLD.epc, EnGwCLD.epc, EnGwFonc.epc | not done | NO
|  | Test 3: Call the tool using both EnGw and NeMo parameters | - check that the tool will ouput all the above mentioned files | not done | NO
|  | Test 4: Call the tool without any of the above mentioned parameters | - check that the tool will not output any of the above mentioned files | not done | NO
TRS.COMCONF.GEN.001(0) | Check the input files | Covered by the tests below |  | not done | NO
TRS.COMCONF.GEN.002(0) | Check the output file | Covered by the tests below |  | not done | NO
TRS.COMCONF.GEN.003(0) | Check the format of the ComCallout file | Can not be tested |  | not done | NO
TRS.COMCONF.GEN.004(0) | Check if a <SPECIFIC-CALLOUT> contains a valid <PDU-REF>, the toll will generate the ComIPduCallout parameter | Test 1: provide to the tool a SPECIFIC-CALLOUT which has the PDU-REF tag set | - check that the tool will set the ComIPduCallout parameter | done | YES
|  | Test 12: provide to the tool a SPECIFIC-CALLOUT that has not the PDU-REF tag set | - check that the tool will not set the ComIPduCallout parameter | done | YES
TRS.COMCONF.GEN.005(0) | Check if a SPECIFIC-CALLOUT contains a valid SYSTEM-SIGNAL-REF, the toll will generate the ComTimeoutNotification and ComNotification parameter | Test 1: provide to the tool a SPECIFIC-CALLOUT which has a valid SYSTEM-SIGNAL-REF tag | - check that the tool will set the ComTimeoutNotification and ComNotification parameter | done | YES
|  | Test 2: provide to the tool a SPECIFIC-CALLOUT which has the <SYSTEM-SIGNAL-REF> tag set, but it does not exist a <SENDER-RECEIVER-TO-SIGNAL-MAPPING> tag from System Generated file which have the same SYSTEM-SIGNAL-REF tag | - check that the tool will not set the ComTimeoutNotification and ComNotification parameter | done | YES
|  | Test 3: provide to the tool a SPECIFIC-CALLOUT that has no SYSTEM-SIGNAL-REF tag | - check that the tool will not set the ComTimeoutNotification and ComNotification parameter | done | YES
TRS.COMCONF.GEN.006(0) | Check the input files | Covered by the tests below |  | not done | NO
TRS.COMCONF.GEN.007(0) | Check the output files | Covered by the tests below |  | not done | NO
TRS.COMCONF.GEN.008(0) | Check the format of the PduRconfiguration script | Can not be tested |  | not done | NO
TRS.COMCONF.GEN.009(0) | Check if each <GATEWAY-MAPPING> will be analysed | Can not be tested |  | not done | NO
TRS.COMCONF.GEN.010(0) | Check if each <SOURCE-I-PDU-REF> and <TARGET-I-PDU-REF> will have the following information present in the messagery file: Cluster, PDU ID, Transmission direction | Test 1: provide to the tool only one <SOURCE-I-PDU-REF>. That source has a CLUSTER and a Transmission direction, but no PDU ID | - check that the EnGw_PduR_Update.xml file will no set the PduRDestPdu parameter | done | YES
|  | Test 2: provide to the tool only one <SOURCE-I-PDU-REF>. That source has a CLUSTER and a PDU ID, but no Transmission direction | - check that the EnGw_PduR_Update.xml file will no set the PduRDestPdu parameter | done | YES
|  | Test 3: provide to the tool only one <SOURCE-I-PDU-REF>. That source has a CLUSTER,a PDU ID and a Transmission direction | - check that the EnGw_PduR_Update.xml file will set the PduRDestPdu parameter | done | YES
TRS.COMCONF.GEN.011(0) | Check if only <SOURCE-I-PDU-REF> that have the transmission direction established will be present in the output file | Test 1: provide to the tool only one <SOURCE-I-PDU-REF>. That source has a Transmission direction | - check that the EnGw_PduR_Update.xml file will set the PduRDestPdu parameter | done | YES
|  | Test 2: provide to the tool only one <SOURCE-I-PDU-REF>. That source has no Transmission direction | - check that the EnGw_PduR_Update.xml file will no set the PduRDestPdu parameter | done | YES
TRS.COMCONF.GEN.012(0) | Check if only the next <GATEWAY-MAPPING> types will be present in the output file: GW-REMOTE-DIAG, GW-FILTERED, GW-LIN-UNCONNECTED, GW-CAN-DIAG | Test 1: provide to the tool all types for <GATEWAY-MAPPING> | - check that the EnGw_PduR_Update.xml file will set the PduRDestPdu parameter for each <SOURCE-I-PDU-REF> | done | YES
|  | Test 2: provide to the tool a different type for <GATEWAY-MAPPING> | - check that the EnGw_PduR_Update.xml file will not set the PduRDestPdu parameter | done | YES
TRS.COMCONF.GEN.013(0) | Check the format of the PduR.epc file | Can not be tested |  | not done | NO
TRS.COMCONF.GEN.014(0) | Check if each <GATEWAY-MAPPING> will be analysed | Can not be tested |  | not done | NO
TRS.COMCONF.GEN.015(0) | Check if each <SOURCE-I-PDU-REF> and <TARGET-I-PDU-REF> will have the following information present in the messagery file: PDU ID and Transmission direction | Test 1: provide to the tool only one <GATEWAY-MAPPING> which has a <SOURCE-I-PDU-REF> and a <TARGET-I-PDU-REF>. The <SOURCE-I-PDU-REF> has a valid PDU ID, but no Transmission direction. The <TARGET-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. | - check that the routing path will not be created | done | YES
|  | Test 2: provide to the tool only one <GATEWAY-MAPPING> which has a <SOURCE-I-PDU-REF> and a <TARGET-I-PDU-REF>. The <SOURCE-I-PDU-REF> has a valid Transmission direction,but no PDU ID. The <TARGET-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. | - check that the routing path will not be created | done | YES
|  | Test 3: provide to the tool only one <GATEWAY-MAPPING> which has a <SOURCE-I-PDU-REF> and a <TARGET-I-PDU-REF>. The <SOURCE-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. The <TARGET-I-PDU-REF> has a valid PDU ID, but no Transmission direction. | - check that the routing path will not be created | done | YES
|  | Test 4: provide to the tool only one <GATEWAY-MAPPING> which has a <SOURCE-I-PDU-REF> and a <TARGET-I-PDU-REF>. The <SOURCE-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. The <TARGET-I-PDU-REF> has a valid Transmission direction,but no PUD ID. | - check that the routing path will not be created | done | YES
|  | Test 4: provide to the tool only one <GATEWAY-MAPPING> which has a <SOURCE-I-PDU-REF> and a <TARGET-I-PDU-REF>. The <SOURCE-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. The <TARGET-I-PDU-REF> has a valid PDU ID and a valid Transmission direction. | - check that the routing path will be created | done | YES
TRS.COMCONF.GEN.016(0) | Check if only the next <GATEWAY-MAPPING> types will be present in the output file: GW-REMOTE-DIAG, GW-FILTERED, GW-LIN-UNCONNECTED, GW-CAN-DIAG | Test 1: provide to the tool all types for <GATEWAY-MAPPING> | - check that the PduR.epc file will create routing paths for each <GATEWAY-MAPPING> | done | YES
|  | Test 2: provide to the tool a different type for <GATEWAY-MAPPING> | - check that the Pdu.epc file will not create a routing path for <GATEWAY-MAPPING> | done | YES
TRS.COMCONF.GEN.017(0) | Check if for a valid <GATEWAY-MAPPING>, a routing path will be created with the following name: PduRRoutingPath_<source_name>
TRS.COMCONF.GEN.003 | Check that the tool will propely create te PduRRountingTables | Test 1: provide to the tool one valid mapping, where the source frame is referenced in a cluster HS or DIAG | - check that the routing table is created with the correct name - check that the routing path is created with the correct name - check that the destination is created with the correct name and the correct parameters - check that the source is created with the correct name | not done | NO
|  | Test 2: provide to the tool one valid mapping, where the source frame is referenced in a cluster different than LIN, and the target-frame is referenced in a cluster HS or DIAG | - check that the routing table is created with the correct name - check that the routing path is created with the correct name - check that the destination is created with the correct name and the correct parameters - check that the source is created with the correct name | not done | NO
|  | Test 3: provide to the tool one valid mapping of type GW-BTA | - check that the routing table is created with the correct name - check that the routing path is created with the correct name - check that the destination is created with the correct name and the correct parameters - check that the source is created with the correct name | not done | NO
|  | Test 4: provide to the tool one valid mapping of type GW-ISACTIVE | - check that the routing table is created with the correct name - check that the routing path is created with the correct name - check that the destination is created with the correct name and the correct parameters - check that the source is created with the correct name | not done | NO
|  | Test 5: provide to the tool one valid mapping of type CCL-DIAG-GW | - check that the routing table is created with the correct name - check that the routing path is created with the correct name - check that the destination is created with the correct name and the correct parameters - check that the source is created with the correct name | not done | NO
|  | Test 6: provide to the tool one valid mapping of type GW-FILTERED, where the target frame and the source frame are+C60 referenced in a cluster of type FD | - check that the routing table is not created | not done | NO
TRS.COMCONF.GEN.005 | Check that the tool will create the CanTp PDUs | Test 1: provide to the tool one NAD configured in a 2.1 LIN network, and one Diag tool configured | -check that the four PDUs will be created for the specified NAD - check that the naming rule is respected for each PDU | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 1.3 LIN network, and one Diag tool configured | - check that no PDUs are created | not done | NO
TRS.COMCONF.GEN.006 | Check that the tool will create the LinTp PDUs | Test 1: provide to the tool one NAD configured in a 2.1 LIN network | -check that the four PDUs will be created for the specified NAD - check that the naming rule is respected for each PDU | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 1.3 LIN network | - check that no PDUs are created | not done | NO
TRS.COMCONF.GEN.007 | Check that the tool will create the LIN type 2.1 PDUs | Test 1: provide to the tool one 2.1 LIN, and one Diag tool configured | -check that the two PDUs will be created for the specified NAD - check that the naming rule is respected for each PDU | not done | NO
|  | Test 2: provide to the tool one 1.3 LIN, and one Diag tool configured | - check that no PDUs are created | not done | NO
TRS.COMCONF.GEN.008 | Check that the tool will create the CanIf PDUs | Test 1: provide to the tool one NAD configured in a 1.3 LIN network, and one Diag tool configured | -check that the four PDUs will be created for the specified NAD - check that the naming rule is respected for each PDU | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 2.1 LIN network, and one Diag tool configured | - check that no PDUs are created | not done | NO
TRS.COMCONF.GEN.009 | Check that the tool will create the LinIf PDUs | Test 1: provide to the tool one NAD configured in a 1.3 LIN network | -check that the four PDUs will be created for the specified network - check that the naming rule is respected for each PDU | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 2.1 LIN network | - check that no PDUs are created | not done | NO
TRS.COMCONF.GEN.00B | Check that the CanTp frames are created | Test 1: provide to the tool one NAD configured in a 2.1 LIN network, and one Diag tool configured | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 1.3 LIN network, and one Diag tool configured | - check that no frame is created for the specified NAD | not done | NO
TRS.COMCONF.GEN.00C | Check that the LinTp frames are created | Test 1: provide to the tool one NAD configured in a 2.1 LIN network | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 1.3 LIN network | - check that no frame is created for the specified NAD | not done | NO
TRS.COMCONF.GEN.00D | Check that the CanIf frames are created | Test 1: provide to the tool one NAD configured in a 1.3 LIN network, and one Diag tool configured | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 2.1 LIN network, and one Diag tool configured | - check that no frame is created for the specified NAD | not done | NO
TRS.COMCONF.GEN.00E | Check that the LinIf frames are created | Test 1: provide to the tool one NAD configured in a 2.1 LIN network | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one NAD configured in a 1.3 LIN network | - check that no frame is created for the specified NAD | not done | NO
TRS.COMCONF.GEN.01F | Check that CCLD gateway frames are created | Test 1: provide one valid mapping of type CCL-DIAG-GW, where the source and target frames are referenced in the cluster | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one valid mapping with type different than CCL-DIAG-GW, where the source and target frames are referenced in the cluster | - check that no frames are created for the specified mapping | not done | NO
TRS.COMCONF.GEN.02F | Check that CCB gateway frames are created | Test 1: provide one valid mapping of type GW-BTA, where the source and target frames are referenced in the cluster | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one valid mapping with type different than GW-BTA, where the source and target frames are referenced in the cluster | - check that no frames are created for the specified mapping | not done | NO
TRS.COMCONF.GEN.03F | Check that CCD gateway frames are created | Test 1: provide one valid mapping of type GW-CAN-DIAG, where the source and target frames are referenced in the cluster | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one valid mapping with type different than GW-CAN-DIAG, where the source and target frames are referenced in the cluster | - check that no frames are created for the specified mapping | not done | NO
TRS.COMCONF.GEN.04F | Check that Fonc gateway frames are created | Test 1: provide one valid mapping of type GW-ISACTIVE, where the source and target frames are referenced in the cluster | - check that the request frame is created and has the correct name - check that the response frame is created and has the correct name | not done | NO
|  | Test 2: provide to the tool one valid mapping with type different than GW-ISACTIVE, where the source and target frames are referenced in the cluster | - check that no frames are created for the specified mapping | not done | NO
CHECK.XML | Check the tool behavior in case of xml file not well formed | Provide to the tool one ".xml" or ".arxml" file that is not correct (tags not properly closed, multiple roots, etc) | - check that no file is generated | not done | NO